## Tasks
Task	Priority	Estimated Hours	Status	Is Training?	Notes
Puzzle template implementation	Alpha	5	DONE	Yrs
Dynamic Puzzle Instance Implementation	Alpha	5	TODO	No
Dynamic Puzzle Option Implementation	Alpha	3	TODO	Yes
Mobile theme fit and finish	Alpha	2	IN PROGRESS	No
Invitations	Alpha	2	DONE	No
Forgotten password	Alpha	3	DONE	No
Puzzle catalogue	Alpha	3	IN PROGRESS	No
Search (Elastica)	Beta	5	TODO	No
User edit	Alpha	3	DONE	No
Catpcha	Alpha	1	TODO
Blocked E-Mails	Alpha	1	DONE
Report Bug	Alpha	3	DONE
Maintenance Mode	Alpha	1	DONE
User Admin	Alpha	1	DONE
Bug Report admin	Alpha	1	DONE
Cookie Policy	Alpha	1	TODO
Unit Tests	Alpha	1	IN PROGRESS
Inline SVGs	Beta	1	TODO
Mailer	Alpha	1	DONE
Inject build environment to APIs	Alpha	1	DONE		Probably needs tweaking. Very dirty ATM.
Upload Images	Alpha	1	TODO
Add templates from puzzle screen	Beta	1	TODO
User Promotion Command	Alpha	1	DONE
Tabs Resizing event	Alpha	2	TODO

## Bugs & Improvements
Task	Priority	Estimated Hours	Status	Bug/Improvement	Notes