## Tasks
Task	Priority	Estimated Hours	Status	Is Training?	Notes
Puzzle template implementation	Alpha	5	DONE	Yes
Dynamic Puzzle Instance Implementation	Alpha	5	TODO	No
Dynamic Puzzle Option Implementation	Alpha	3	TODO	Yes
Mobile theme fit and finish	Alpha	2	IN PROGRESS	No
Invitations	Alpha	2	DONE	No
Forgotten password	Alpha	3	DONE	No
Puzzle catalogue	Alpha	3	IN PROGRESS	No
Search (Elastica)	Beta	5	TODO	No
User edit	Alpha	3	DONE	No
Catpcha	Alpha	1	DONE	No
Blocked E-Mails	Alpha	1	DONE	Yes
Report Bug	Alpha	3	DONE	No
Maintenance Mode	Alpha	1	DONE	No
User Admin	Alpha	1	DONE	No
Bug Report admin	Alpha	1	DONE	No
Cookie Policy	Alpha	1	DONE	No
Unit Tests	Alpha	1	IN PROGRESS	No
Inline SVGs	Beta	1	DONE	No
Mailer	Alpha	1	DONE	No
Inject build environment to APIs	Alpha	1	DONE	No	Probably needs tweaking. Very dirty ATM.
Upload Images	Alpha	1	TODO	Maybe
Add templates from puzzle screen	Beta	1	TODO	No
User Promotion Command	Alpha	1	DONE	Yes
Tabs Resizing event	Alpha	2	DONE	No
Check all registration and forgotten password emails for mail.conundrumcodex.com sender domain	Alpha	1	DONE	No
Remove dummy Slideshow element.	Alpha	1	DONE	No
Set up Backup scripts	Alpha	1	DONE	No
Rotate credentials	Alpha	1	TODO	No
Filtering suspects	Beta	3	TODO	No
Remove test pages	Alpha	1	TODO	No
Delete User	Alpha	1	DONE	No
Five Game Limit	Alpha	3	DONE	No
API Security	Alpha	3	TODO	Yes
PHPStan Hardening	Alpha	8	TODO	Yes

## Bugs & Improvements
Task	Priority	Estimated Hours	Status	Bug/Improvement	Notes
User card		1	DONE	BUG	Fix layout in Mobile View
Games Gard		1	DONE	BUG	Fix layout in Mobile View
BTN GROUP		1	DONE	BUG	btn group column layout
Alphabet hid mobile		1	DONE	Improvement	Hide the alphabet jump view in Mobile.
Fading notifications		1	DONE	Improvement	Make notifications fade automatically.